## Example
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 1
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 12 | 11 | 10 | 8 | 83.33% | 72.73% | 66.67%
James Pogue | 12 | 14 | 14 | 12 | 116.7% | 85.71% | 100%
Ted Danson | 12 | 6 | 4 | 3 | 33.33% | 50% | 25%
Team Totals: | 36 | 31 | 28 | 23 | 77.78% | 74.19% | 63.89%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint4
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 4
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
James Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 3 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 4 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 5 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint5
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 5
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
James Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 3 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 4 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 5 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint6
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 6
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
James Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 3 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 4 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 5 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint7
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 7
Team: | Team Fun
Scrum Master: | Eric Pogue
Product Owner | James Pogue
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Eric Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
James Pogue | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 3 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 4 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 5 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Member 6 | 1 | 1 | 1 | 1 | 100% | 100% | 100%
Team Totals: | 6 | 6 | 6 | 6 | 100% | 100% | 100%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | JP |  | January 29, 2023 @ 11:58 pm
Scrum Master | EJP |  | January 29, 2023 @ 11:59 pm
Final Signoff | Initial |  | Date
Product Owner | JP |  | January 30, 2023 @ 2:06 pm
Scrum Master | EJP |  | January 30, 2023 @ 2:07 pm

## Sprint2 Stone Ocean
Capacity, Commited, Effort, and Delivered Metric
Sprint: | 2
Team: | Stone Ocean
Scrum Master: | Nicholas Jones
Product Owner | Ryan Wandke
Name | Estimated Capacity (hours) | Story Points Committed | Hours Worked/Effort (hours) | Story Points Delivered | Capacity to Effort (%) | Committed to Delivered (%) | Capacity to Delivered (%)
Juno Tyne | 12 | 12 | 8 | 6 | 66.67% | 50% | 50%
Ryan Wandke | 12 | 14 | 12 | 14 | 100% | 100% | 116.7%
Nicholas Jones | 12 | 13 | 9 | 9 | 75% | 69.23% | 75%
Fawz Manzoor | 12 | 15 | 8 | 15 | 66.67% | 100% | 125%
Team Totals: | 48 | 54 | 37 | 44 | 77.08% | 81.48% | 91.67%
Preliminary Signoff | Initial |  | Date/Time
Product Owner | RW |  | Sep 11 2026
Scrum Master | NJ |  | Sep 11 2026; 9:07 PM
Final Signoff | Initial |  | Date
Product Owner | RW |  | Sept 20 2026
Scrum Master | NJ |  | Sept 20 2026; 9:16 PM